## Line_Item_Detail
Account_Code | Category | Department | Line_Item | Budget_Amount | Actual_Amount | PO_Committed | Invoice_Paid | Source_Reference
1100 | ATL | Story & Rights | Screenplay Purchase | 80550 | 80550 | 80550 | 80550 | WGA Schedule of Minimums 2023 Low Budget Original Screenplay
1200 | ATL | Producer | Executive Producer Fee | 67420 | 67420 | 67420 | 67420 | BLS OEWS May 2023 SOC 27-2012 CA median annual $101,130
1201 | ATL | Producer | Line Producer Fee | 81696 | 81696 | 81696 | 81696 | DGA Basic Agreement 2023 UPM weekly rate $6,808
1300 | ATL | Director | Director Fee - Prep (4 wks) | 86028 | 86028 | 86028 | 86028 | DGA Basic Agreement 2023 prep rate $21,507/wk x 4
1301 | ATL | Director | Director Fee - Shoot (6 wks) | 144690 | 144690 | 144690 | 144690 | DGA Basic Agreement 2023 shoot rate $24,115/wk x 6
1400 | ATL | Cast | Lead Actor #1 (6 wks) | 44832 | 44832 | 44832 | 44832 | SAG-AFTRA 2023 Low Budget weekly $7,472 x 6
1401 | ATL | Cast | Lead Actor #2 (6 wks) | 44832 | 44832 | 44832 | 44832 | SAG-AFTRA 2023 Low Budget weekly $7,472 x 6
1402 | ATL | Cast | Supporting Cast (3 actors, 15 days ea) | 96795 | 96795 | 96795 | 96795 | SAG-AFTRA 2023 Low Budget day $2,151 x 15d x 3
1500 | ATL | Fringes-ATL | ATL Payroll Tax & P&H (16%) | 107253 | 107253 | 107253 | 107253 | Blended SAG 19.1% DGA 13.5% WGA 18% avg ~16%
2100 | BTL-Prod | Production Staff | Unit Production Manager (6 wks) | 40848 | 40848 | 40848 | 40848 | DGA Basic Agreement 2023 UPM $6,808/wk x 6
2101 | BTL-Prod | Production Staff | 1st Assistant Director (6 wks) | 35088 | 35088 | 35088 | 35088 | DGA Basic Agreement 2023 1st AD $5,848/wk x 6
2200 | BTL-Prod | Camera | Director of Photography (7 wks) | 26208 | 26208 | 26208 | 26208 | IATSE Local 600 DP scale $3,744/wk x 7
2201 | BTL-Prod | Camera | Camera Operator (6 wks) | 18906 | 18906 | 18906 | 18906 | IATSE Local 600 Camera Op $3,151/wk x 6
2202 | BTL-Prod | Camera | 1st AC / Focus Puller (6 wks) | 16188 | 16188 | 16188 | 16188 | IATSE Local 600 1st AC $2,698/wk x 6
2203 | BTL-Prod | Camera | Camera Equipment Rental (30 days) | 135000 | 145000 | 145000 | 138000 | ARRI Alexa Mini LF package ~$4,500/day (Panavision 2023)
2300 | BTL-Prod | Art Department | Production Designer (8 wks) | 17600 | 17600 | 17600 | 17600 | BLS OEWS May 2023 SOC 27-1011 CA $114,380/yr weekly
2302 | BTL-Prod | Art Department | Set Construction (4 crew, 6 wks) | 44650 | 52000 | 52000 | 48000 | IATSE Local 44 journeyman rate $46.51/hr
2600 | BTL-Prod | Grip & Electric | Gaffer (6 wks) | 15786 | 15786 | 15786 | 15786 | IATSE Local 728 gaffer scale $52.62/hr x 50hr/wk
2601 | BTL-Prod | Grip & Electric | Key Grip (6 wks) | 14514 | 14514 | 14514 | 14514 | IATSE Local 80 key grip scale $48.38/hr x 50hr/wk
2602 | BTL-Prod | Grip & Electric | G&E Equipment Rental (30 days) | 105000 | 115000 | 115000 | 108000 | Industry standard G&E package ~$3,500/day
2700 | BTL-Prod | Sound | Sound Mixer (6 wks) | 17337 | 17337 | 17337 | 17337 | IATSE Local 695 mixer scale $57.79/hr x 50hr/wk
2800 | BTL-Prod | Locations | Location Fees (30 days) | 84150 | 92000 | 92000 | 88000 | FilmLA 2023 permit $805/day + avg location $2,000/day
2950 | BTL-Prod | Catering | Craft & Catering (30 days, 40 crew) | 54000 | 58000 | 58000 | 56000 | Industry standard catering $45/person/day x 40 x 30
2990 | BTL-Prod | Fringes-BTL | BTL Payroll Tax & P&H (23.6%) | 63800 | 68000 | 68000 | 66000 | IATSE/IBEW P&H 14.5% + payroll tax 9.1% = 23.6%
3100 | Post | Editorial | Editor (12 wks) | 21912 | 21912 | 21912 | 21912 | BLS OEWS May 2023 SOC 27-4032 CA $94,920/yr weekly
3200 | Post | VFX | Visual Effects (100 shots) | 50000 | 65000 | 65000 | 58000 | VES 2023 indie rate survey ~$500/shot low-complexity
3300 | Post | Sound Post | Sound Design & Mix | 17500 | 18000 | 18000 | 17500 | Industry standard mix stage $3,500/day x 5 days
3301 | Post | Sound Post | Music Score (package) | 25000 | 25000 | 25000 | 25000 | BMI/ASCAP indie film score package typical $25K
3400 | Post | Finishing | Color Grading & DI | 15000 | 15000 | 15000 | 15000 | Technicolor/Company 3 indie feature DI rate ~$15K
4100 | Other | Insurance | Production Insurance (3%) | 42000 | 44000 | 44000 | 43000 | Industry standard production insurance 3% of budget
4200 | Other | Legal | Legal & Clearances (60 hrs) | 27000 | 29000 | 29000 | 28000 | Entertainment attorney published rate $450/hr x 60hrs
4600 | Other | Contingency | Contingency (10%) | 140000 | 0 | 0 | 0 | Industry standard 10% contingency reserve

## Budget_vs_Actual
Category | Total_Budget | Total_Actual | Variance_Dollar | Variance_Pct | Total_Committed | Total_Paid | Remaining_Committed | EAC_Estimate_at_Completion | ETC_Estimate_to_Complete | Status_Flag
ATL
BTL-Prod
Post
Other
GRAND TOTAL
Flag Rules:
OVER_BUDGET if Variance_Pct > 5%
ON_TRACK if -5% <= Variance_Pct <= 5%
UNDER_BUDGET if Variance_Pct < -5%

## Department_Summary
Department | Budget_Total | Actual_Total | Variance_Dollar | Variance_Pct | Line_Item_Count | Largest_Overrun_Item | Largest_Overrun_Amount
Art Department
Camera
Cast
Catering
Contingency
Director
Editorial
Finishing
Fringes-ATL
Fringes-BTL
Grip & Electric
Insurance
Legal
Locations
Producer
Production Staff
Sound
Sound Post
Story & Rights
VFX

## Contingency_Tracker
Metric | Value
Original Budget (excl. contingency)
Contingency Budget
Total Budget (incl. contingency)
Total Actual Spend
Total Overrun (excl. contingency)
Contingency Used
Contingency Remaining
Contingency Utilization %
Projected Final Cost
Budget Health